**Sprint Plan 3**

**Team Number: *82 (Project I.T.)***

|  |  |
| --- | --- |
| **Student Number** | **Team Member Name** |
| N9163166 | Tess Nash |
| N9412719 | Peipei Zhang |
| N7294352 | Jiyoung Choi |
| N9169008 | Kris Kingston |
| N8922713 | Se Jun Ahn |
| N9530941 | Khor Kent Lie |
| N9058575 | Sahib Onkar Singh |

***Tutor: Dr. Venkat Venkatachalm***

***Project: Community Centre***

***Version: 1.0***

***Date: 21st September, 2016***

# Sprint 3

*Total Story Points: 3 (Incomplete Stories from R1) and 29 (Stories from Sprint 3)*

## *Current Velocity: 20-24 (Based on progress from Sprints 1 and 2)*

## *Total Hours (Estimated – For Sprint 3 Tasks): 43 Total Hours (Actual): 50*

## STORIES TO COMPLETE FROM RELEASE 1:

## Story 10: Tracking Member and Volunteer Details – Top Priority to Complete before Starting on Sprint 3 Stories (T05 Incomplete)

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T05\* | Develop JavaScript API to track the events | 2 | 3 |
| T06 | Restrict access to admins only | 1 | 1 |
| T07 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 1 Total Hours:* | *4* | *5* |

## Story 11: Accessibility of Features – Top Priority to Complete before Starting on Sprint 3 Stories (T18 Incomplete)

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T16 | Have Navigation bar for all pages | 3 | 3 |
| T17 | Have a different navigation bar for admin and president | 2 | 3 |
| T18\* | President will be able to see to track the event link and finance link in the navigation bar | 2 | 4 |
| T19 | Restrict access for authorised office admins only | 2 | 2 |
| T20 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 8 Total Hours:* | *10* | *13* |

\* = Tasks were yet to be completed, however were completed by the conclusion of Sprint 3

## RELEASE 2 – SPRINT 3 STORIES

## Story 01: Event Communication

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T01 | Use JavaScript code to enable user to press a button and generate an automatic email which is then sent to General Member when the current date is three days until the event | 1 | 1 |
| T02 | Develop social media pages and have links to the pages in the home page and sub-menus | 1 | 2 |
| T03 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 1 Total Hours:* | *3* | *4* |

## Story 03: Communication Between Members

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T04 | Have the database for users have an email column and have a relation for chats and messages | 1 | 2 |
| T05 | Outline the respective fields to be access in its own sub-menu page | 2 | 2 |
| T06 | Develop this to be a separate entity to be accessed in multiple sub-menus | 1 | 2 |
| T07 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 4 Total Hours:* | *5* | *7* |

## Story 09: Cost Estimation of Event

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T08 | Have code to estimate the costs that show in the events development page | 2 | 3 |
| T09 | Have this shown to the volunteers who are working at the event | 3 | 4 |
| T10 | Have this view for the committee members involved | 3 | 4 |
| T11 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 4 Total Hours:* | *9* | *12* |

## Story 26: Communication Between Volunteers

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T12 | Develop comment relation that is dependant on the news article relation | 1 | 2 |
| T13 | Have all news articles have a comment interface | 7 | 7 |
| T14 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 4 Total Hours:* | *9* | *10* |

## Story 27: Selling Items Online to Raise Funds for Centre

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T15 | Have a user relation connect to items relation in the database | 2 | 2 |
| T16 | Have images and good design for the items user interface | 4 | 4 |
| T17 | Use JavaScript to mouse over options | 10 | 10 |
| T18 | Verify story is complete (acceptance test) | 1 | 1 |
|  | *Story Points: 16 Total Hours:* | *17* | *17* |