## Slide 1: Team 82 – Community82 Release 1 (Sprints 1 and 2)
Team Members:
Tess Nash, Kris Kingston, Peipei Zhang, Ji Young Choi, Se Jun Ahn, Kent Lie and Sahib Onkar Singh
Website Link:
http://54.206.25.253/pages/index.php

## Slide 2: Release 1 Overview: Expectations
What we wanted to achieve at the end of Release 1:
  Sprint 1 – 26 Story Points:
    Had 5 Stories that we wanted to have completed at the end of the Sprint
      Aimed to have all of these stories completed so we could move onto the next sprint
  Sprint 2 – 22 Story Points:
    Had 4 Stories that we wanted to have completed at the end of the Sprint
      Aimed to have all of these stories completed so we could move onto the next sprint and the next Release

## Slide 3: Release 1 Overview: Actuals
What we actually achieved at the end of Release 1:
  Sprint 1:
    Achieved 4 out of 5 Stories (30 out of 32 Story Points Completed)
      At the end of the last Sprint, we believed that it was only a minor issue that needed to be fixed to declare this story complete
      However, upon further investigation, we have realised there are more tasks than we had originally predicted that need to be completed in order to fully complete this story, and at the end of Release 1 we have found that there is one Task that needs to be finalised before moving on to the next release
  Sprint 2:
    Achieved 3 out of 4 Stories (20 out of 22 Story Points Completed)
      Similar with Sprint 1, upon further investigation, there was one Task that needs to be finalised in order for this story to be fully completed

## Slide 4: Sprint 1 – Ideal Progression
User Story ID and Description | Story Points | No. of Tasks Involved | Estimated Time Taken (Hours)
S04: Updating Member’s Details Themselves | 8 | 4 | 9
S05: Resetting Member’s Passwords | 4 | 4 | 6
S06: Leaving the Organisation – Position Termination | 8 | 3 | 9
S08: Creating, Modifying and Deleting Events | 4 | 4 | 5
S11: Accessibility of Features | 8 | INCOMPLETE (One Task to Finalise) | 

## Slide 5: Sprint 1 – Actual Progression
User Story ID and Description | Story Points | No. of Tasks Involved | Actual Time Taken (Hours)
S04: Updating Member’s Details Themselves | 8 | 4 | 9
S05: Resetting Member’s Passwords | 4 | 4 | 6
S06: Leaving the Organisation – Position Termination | 8 | 3 | 10
S08: Creating, Modifying and Deleting Events | 4 | 4 | 6
S11: Accessibility of Features | 8 | INCOMPLETE (One Task to Finalise) | 

## Slide 6: Sprint 2 – Ideal Progression
User Story ID and Description | Story Points | No. of Tasks Involved | Estimated Time Taken (Hours)
S07: Online Confirmation of Attendance | 4 | 4 | 7
S10: Tracking Member and Volunteer Details | 1 | INCOMPLETE (One Task to Finalise) | 
S16: Online Sign-Up to Volunteer at Events | 16 | 5 | 20
S23: Editing Other User’s Information | 1 | 3 | 4

## Slide 7: Sprint 2 – Actual Progression
User Story ID and Description | Story Points | No. of Tasks Involved | Estimated Time Taken (Hours)
S07: Online Confirmation of Attendance | 4 | 4 | 9
S10: Tracking Member and Volunteer Details | 1 | INCOMPLETE (One Task to Finalise) | 
S16: Online Sign-Up to Volunteer at Events | 16 | 5 | 24
S23: Editing Other User’s Information | 1 | 3 | 6

## Slide 8: Ideal Overall Burndown Chart
Chart: Overall Release Burndown Chart
| 0.0 | 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0
Story Points | 139 | 113 | 91 | 68 | 40 | 30 | 22 | 12 | 0

## Slide 9: Sprint 1 Burndown Chart
Chart: Time Taken (Hours)
| 0.0 | 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 17.0 | 18.0 | 19.0 | 20.0 | 21.0 | 22.0 | 23.0 | 24.0 | 25.0 | 26.0 | 27.0 | 28.0 | 29.0 | 30.0 | 31.0 | 32.0 | 33.0 | 34.0 | 35.0 | 36.0 | 37.0 | 38.0 | 39.0 | 40.0 | 41.0 | 42.0 | 43.0 | 44.0
Ideal Tasks Remaining | 20 | 19 | 19 | 18 | 18 | 17 | 17 | 16 | 16 | 16 | 15 | 14 | 13 | 13 | 12 | 11 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 8 | 7 | 7 | 6 | 6 | 5 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 0
Actual Tasks Remaining | 20 | 19 | 19 | 18 | 18 | 18 | 18 | 17 | 17 | 17 | 16 | 16 | 16 | 15 | 14 | 13 | 13 | 12 | 12 | 11 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 7 | 7 | 6 | 5 | 5 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0

## Slide 10: Sprint 2 Burndown Chart
Chart: Time Taken (Hours)
| 0.0 | 1.0 | 2.0 | 3.0 | 4.0 | 5.0 | 6.0 | 7.0 | 8.0 | 9.0 | 10.0 | 11.0 | 12.0 | 13.0 | 14.0 | 15.0 | 16.0 | 17.0 | 18.0 | 19.0 | 20.0 | 21.0 | 22.0 | 23.0 | 24.0 | 25.0 | 26.0 | 27.0 | 28.0 | 29.0 | 30.0 | 31.0 | 32.0 | 33.0 | 34.0 | 35.0 | 36.0 | 37.0 | 38.0 | 39.0 | 40.0 | 41.0 | 42.0 | 43.0
Ideal Tasks Remaining | 15 | 14 | 13 | 13 | 12 | 11 | 11 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 8 | 7 | 6 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 2 | 0
Actual Tasks Remaining | 15 | 14 | 14 | 13 | 13 | 13 | 12 | 11 | 11 | 11 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0

## Slide 11: Release 1 Burndown Chart
Chart: Time Taken (Hours)

## Slide 12: Goals for the Next Release: Release 2 (Sprints 3 and 4)
Aim to finalise the incomplete user stories
  This will be our top priority to ensure that these stories are complete before starting on the completion of the stories in Sprint 3
We will need to readjust our Sprint Plans
  Sprint 3 will need to be readjusted in order to accommodate the incomplete user stories from Release 1
  Sprint 4 will also more than likely need to be readjusted to accommodate for these changes and accommodate the overflow of stories from Sprint 3
    I.e. readjust the plans to make room to complete the incomplete Release 1 stories and successfully complete the stories from Release 2 (Sprints 3 and 4)

## Slide 13: Goals for the Next Release: Sprint 3 (Overflow of Stories from Release 1)
User Story ID and Description | Story Points | No. of Tasks Involved | Estimated Time Taken (Hours)
S10: Tracking Member and Volunteer Details | 1 | 3 | 4
S11: Accessibility of Features | 8 | 5 | 10

## Slide 14: Goals for the Next Release: Sprint 3 – Stories from Sprint 3 that we’re aiming to complete
User Story ID and Description | Story Points | No. of Tasks Involved | Estimated Time Taken (Hours)
S01: Event Communication | 1 | 3 | 3
S03: Communication Between Members | 4 | 4 | 5
S09: Cost Estimation of Event | 2 | 4 | 4
S26: Communication Between Volunteers | 8 | 5 | 10
S27: Selling Items Online to Raise Funds for Centre | 8 | 3 | 9