## Slide 1: Team 82 – Community82 End of Sprint 3 Peer Review Demonstration
Team Members:
Tess Nash, Kris Kingston, Peipei Zhang, Ji Young Choi, Se Jun Ahn, Kent Lie and Sahib Onkar Singh
Website Link:
http://54.206.25.253/pages/index.php

## Slide 2: Procedure of All Sprints – BPMN Model

## Slide 3: Sprint 3 – Expected Progress
What we wanted to achieve at the conclusion of Sprint 3:
  Finish off the completion of overflow of stories from Release 1
    Has 2 Stories that were an overflow from the previous Release that needed to be completed before we could move on to Sprint 3 Stories
  Sprint 3 – 29 Story Points:
    Had 5 Stories that we wanted to have completed at the end of the Sprint
      Aimed to have all of these stories completed so we could move onto the next sprint

## Slide 4: Sprint 3 – Actual Progress
What we actually achieved at the conclusion of Sprint 3:
  Finished off the completion of overflow of stories from Release 1
    Finalised the 2 Stories that were an overflow from the previous Release (only had minor issues with the tasks that needed to be finalised)
  Sprint 3 – 29 Story Points:
    Completed 3 out of 5 Stories that we wanted to have completed at the end of the Sprint
      Some tasks still need to be finalised in order for them to be classified as 100% complete (minor errors with certain tasks – 85-90% completion rate thus far)

## Slide 5: Sprint 3 – Ideal Task Progression
User Story ID and Description | Story Points | No. of Tasks Involved | Estimated Time Taken (Hours)
S01: Event Communication | 1 | 3 | 3
S03: Communication Between Members | 4 | 4 | 5
S09: Cost Estimation of Event | 4 | 4 | 9
S26: Communication Between Volunteers | 4 | 3 | 9
S27: Selling Items Online to Raise Funds for Centre | 16 | 4 | 17

## Slide 6: Sprint 3 – Actual Task Progression
User Story ID and Description | Story Points | No. of Tasks Involved | ActualTime Taken (Hours)
S01: Event Communication | 1 | 3 | 4 (so far)
S03: Communication Between Members | 4 | 4 | 7 (so far)
S09: Cost Estimation of Event | 4 | 4 | 12
S26: Communication Between Volunteers | 4 | 3 | 10
S27: Selling Items Online to Raise Funds for Centre | 16 | 4 | 17
NOTE: Some tasks are experiencing some errors with execution, however we can still class these tasks as being completed with a 85% completion rate for stories; the stories highlighted are yet to be completed, with only 1 or 2 tasks needing to be finalised in order for them to be classified as complete

## Slide 7: Sprint 3 Burndown Chart
Chart: Time Taken (Hours)
Ideal Tasks Remaining | 18 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 16 | 16 | 16 | 16 | 15 | 15 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 12 | 11 | 10 | 10 | 10 | 9 | 9 | 9 | 8 | 8 | 7 | 6 | 5 | 5 | 4 | 3 | 2 | 1 | 0
Actual Tasks Remaining | 18 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 16 | 16 | 16 | 16 | 15 | 15 | 14 | 13 | 13 | 12 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 8 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 0

## Slide 8: Goals for the Next Sprint – Sprint 4:
Aim to finalise any incomplete user stories from Sprint 3 (Story ID 1 and Story ID 3)
  This will be our top priority to ensure that these stories are complete before starting on Sprint 4
  Once these tasks have been finalised, we will start on completing stories from Sprint 4
Continue progression on Acceptance Testing reports
Continue progression on User Testing to gain feedback from potential users